## Improvement Plan
Instructions: This template plan lists the DSPT outcomes where the organisation did not reach the expected acheivement levels.
In order to complete your assessment, please complete this improvement plan, including the actions you are going to complete and the target completion date
You should cross reference this plan with your DSPT Audit report to ensure all actions required to reach the expected acheivement level for the outcomes are included.
You should save a copy, and when prompted, upload the file to the Data security and Protection Toolkit, to complete your publication.
More information: | https://dsptoolkit.nhs.uk/News/improvement-plans-24-25
Date updated | Organisation Name | Organisation Code | Main Contact (update if required) | DSPT Outcome | Indicator of good practice (IGP) reference if relevant | What actions do you plan to take to meet the requirement? Please provide details of any milestones. This should include any action required to ensure the activity is funded and resourced to achieve the planned completion date. Please use an indivdual row for each action. | Action Owner | Priority (High, Medium, Low) | Are there any dependencies or blockers that have prevented completion of this evidence item? (Please provide details) | Does the action have an internal reference number such as Audit action or risk register reference? | Initial Planned Completion date A date is required for improvement plan to be completed | Updated Planned completion date Any amendements to dates for the improvement plan to be completed. | Status (Not Started/Complete/Work on-going/No further work planned) | Provide the plan to achieve the outstanding actions required to meet the outcome/or link to a more detailed plan | (To be completed in September) September 2025 Update Is the delivery date still valid, if not please provide an updated date | (To be completed in September) September 2025 Comments | (To be completed in December) December 2025 Update Is the delivery date still valid, if not please provide an updated date | (To be completed in December) December 2025 Comments
2025-06-02 | NHS Masham Foundation Trust | R11 | Paul Jones | A2.a | PA#4 | 01/07/25 Update Information Risk management policy to include threshold for communicating serious risk management actions to senior stakeholders. | Paul Jones - Cyber Lead | Medium | Policy Approval process backlog; management resource availability | Datix CS124/01 | 2025-07-01 |  | Work on-going | Detailed project plan attached at A2a.DSPT 24-25
2025-06-02 | NHS Masham Foundation Trust | R11 | Paul Jones | A2.a | PA#4 | 01/07/25 Funding secured for specialist communications resource; 07/07/25 Specialist communications resource onboarded; 01/08/25 Develop Policy to update Communcations Plan | Sarah Smith - Communications Manager | Low | Communication team resource availability | Datix CS124/01 | 2025-08-01 | 15/08/2025 (Date amended due to short delay in onboarding communications resource) | Work on-going | Detailed project plan attached at A2a.DSPT 24-25
2025-06-03 | NHS Masham Foundation Trust | R11 | Paul Jones | A2.a | PA#4 | 15/08/25 Launch Policy to update Communications Plan | Sarah Smith - Communications Manager | Low | Communication team resource availability | Datix CS124/01 | 2025-08-15 | 21/08/2025 (Date amended due to short delay in onboarding communications resource) | Work on-going | Detailed project plan attached at A2a.DSPT 24-25
2025-06-02 | NHS Masham Foundation Trust | R11 | Paul Jones | A2.a | PA#4 | 01/09/2025 Information Risk Management Policy operational. | Paul Jones - Cyber Lead | Medium | Corporate Governance resouce | Datix CS124/01 | 2025-09-01 |  | Work on-going | Detailed project plan attached at A2a.DSPT 24-25
2025-06-02 | NHS Masham Foundation Trust | R11 | Paul Jones | A2.a | PA#4 | 01/11/2025 Review of communications to senior stakeholders. | Suzy Chen - Information Governance lead | Medium | Dependancy on previous actions | N/A | 2025-11-01 |  | Not Started | Detailed project plan attached at A2a.DSPT 24-25
2025-06-02 | NHS Masham Foundation Trust | R11 | Paul Jones | A2.a | PA#4 | 08/11/2025 Sign off Outcome as complete. | Paul Jones - Cyber Lead | Medium | Dependancy on previous actions | N/A | 2025-11-08 |  | Not Started | Detailed project plan attached at A2a.DSPT 24-25
2025-06-02 | NHS Masham Foundation Trust | R11 | Paul Jones | B6.b | A#1 | 01/08/2025 Attend Board to provide Board training Briefing. Identified in Training Needs Analysis (TNA) but not complete for some Board members in line with twelve month requirement in TNA. | Paul Jones - Cyber Lead | High | Board slot availability. (Board Secretary has confirmed Board slot) | Datix CS125/01 | 2025-08-01 |  | Work on-going | Board slot booked Materials reviewed in readiness based on latest threats and Examples collated. Run through breifing with SIRO
2025-06-02 | NHS Masham Foundation Trust | R11 | Paul Jones | B6.b | A#2 | 10/08/2025 Complete Training form and update Cyber Training Log. | Raj Singh - IT Administrator | Low | Dependancy on previous actions | N/A | 2025-08-10 |  | Not Started | In Raj's work plan for August
2025-06-02 | NHS Masham Foundation Trust | R11 | Suzy Chen - Information Governance lead | E2.a | A#2 | 01/10/2025 Update Contact Centre Training Pack | Suzy Chen - Information Governance lead | Medium | IG Team Availability | Datix CS126/01 | 2025-10-01 |  | Work on-going | Contact Centre Training plan.xls
2025-06-02 | NHS Masham Foundation Trust | R11 | Suzy Chen - Information Governance lead | E2.a | A#2 | 01/10/2025 Book Date to Deliver Contact Centre Training | Raj Singh - IT Administrator | Medium | Contact centre Availability | Datix CS126/01 | 2025-10-01 |  | Work on-going | Contact Centre Training plan.xls
2025-06-02 | NHS Masham Foundation Trust | R11 | Suzy Chen - Information Governance lead | E2.a | A#2 | 01/11/2025 Deliver Contact Centre Training on SARS and FOIs | Suzy Chen - Information Governance lead | Medium | Contact centre Availability | Datix CS126/01 | 2025-11-01 |  | Work on-going | Contact Centre Training plan.xls
2025-06-02 | NHS Masham Foundation Trust | R11 | Paul Jones | B6.b | A#2 | 08/11/2025 Sign off Outcome B6.b as complete. | Paul Jones - Cyber Lead | Medium | Dependancy on previous actions | N/A | 2025-11-08 |  | Not Started | Slot booked by Raj in Paul's Diary
2025-06-02 | NHS Masham Foundation Trust | R11 | Paul Jones | E2.a | A#2 | 08/11/2025 Sign off Outcome E2.a as complete. | Paul Jones - Cyber Lead | Medium | Dependancy on previous actions | N/A | 2025-11-08 |  | Not Started | Slot booked by Raj in Paul's Diary